## Sheet1
Name | Module | Main Task | Subtask | React Page/UI Design | Node/Express Backend | MongoDB Database | Status | Priority
Anil Kumal | Admin Panel | Admin Dashboard | View Admin Overview | Dashboard UI, Sidebar, Navbar | GET /admin/stats | admin_meta | Pending | 0
Anil Kumal | Admin Panel | User Management | Add User | Form UI, Validation | POST /users | users | Pending | 0
Anil Kumal | Admin Panel | User Management | Edit/Delete User | Edit/Delete Buttons, Table UI | PUT/DELETE /users/:id | users | Pending | 0
Anil Kumal | Admin Panel | Settings | Update Admin Info | Settings Page UI | PUT /admin/settings | admin_settings | Pending | 0
Anil Kumal | Notice Module | Add Notice | Create New Notice | Notice Form UI | POST /notices | notices | Pending | 0
Anil Kumal | Notice Module | View/Delete Notices | Notice Table, Delete Button | Table UI | GET/DELETE /notices | notices | Pending | 0
Anil Kumal | Notice Module | Announcement | Post Announcement | Form UI | POST /announcements | announcements | Pending | 0
Anil Kumal | Notice Module | View Announcements | Announcement List | Table/List UI | GET /announcements | announcements | Pending | 0
Anil Kumal | Class Module | Add / Edit / Delete Class | Form UI, Input Validation, Edit/Delete Buttons | POST /classes, PUT /classes/:id, DELETE /classes/:id | classes | Pending | 0
Anil Kumal | Class Module | View / Assign Classes | Table UI, Search & Filter, Assign Dropdown | GET /classes, POST /classes/assign | classes, students | Pending | 0
Anil Kumal | Class Module | Class Validation | Frontend Validation, Backend Validation Logic | Validation Logic | classes | Pending | 0
Nirajan Rokaya | Student Module | Add Student | Registration Form | Form UI, Input Validation | POST /students | students | Pending | 0
Nirajan Rokaya | Student Module | Edit Student | Update Student Details | Edit Form UI | PUT /students/:id | students | Pending | 0
Nirajan Rokaya | Student Module | Delete Student | Remove Student | Delete Button UI | DELETE /students/:id | students | Pending | 0
Nirajan Rokaya | Student Module | View Student List | Table of Students | Table UI, Search & Filter | GET /students | students | Pending | 0
Nirajan Rokaya | Student Module | Student Profile | View Student Details | Profile Page UI | GET /students/:id | students | Pending | 0
Nirajan Rokaya | Student Module | Upload Profile Image | Upload Student Photo | Upload UI, Preview | POST /students/upload | student_files | Pending | 0
Nirajan Rokaya | Student Module | Student Validation | Validate Student Data | Frontend Validation | Backend Validation | students | Pending | 0
Nirajan Rokaya | Student Module | Assign Class | Assign Subjects to Student | Dropdown UI | POST /students/assign | students, subjects | Pending | 0
Abhishek Sapkota | Teacher Module | Add Teacher | Create New Teacher | Form UI, Input Validation | POST /teachers | teachers | Pending | 0
Abhishek Sapkota | Teacher Module | Edit Teacher | Update Teacher Details | Edit Form UI | PUT /teachers/:id | teachers | Pending | 0
Abhishek Sapkota | Teacher Module | Delete Teacher | Remove Teacher | Delete Button UI | DELETE /teachers/:id | teachers | Pending | 0
Abhishek Sapkota | Teacher Module | View Teacher List | Table of Teachers | Table UI, Search & Filter | GET /teachers | teachers | Pending | 0
Abhishek Sapkota | Teacher Module | Teacher Profile | View Teacher Details | Profile Page UI | GET /teachers/:id | teachers | Pending | 0
Abhishek Sapkota | Teacher Module | Teacher Validation | Validate Teacher Data | Frontend Validation UI | Backend Validation Logic | teachers | Pending | 0
Abhishek Sapkota | Teacher Module | Assign Teacher Subjects | Assign Subjects to Teacher | Dropdown UI, Assign Button | POST /teachers/assign | teachers, subjects | Pending | 0
Sabin Devkota | Subject Module | Add Subject | Create New Subject | Form UI, Input Validation | POST /subjects | subjects | Pending | 0
Sabin Devkota | Subject Module | Edit Subject | Update Subject Details | Edit Form UI | PUT /subjects/:id | subjects | Pending | 0
Sabin Devkota | Subject Module | Delete Subject | Remove Subject | Delete Button UI | DELETE /subjects/:id | subjects | Pending | 0
Sabin Devkota | Subject Module | View Subjects | List of Subjects | Table UI, Search & Filter | GET /subjects | subjects | Pending | 0
Sabin Devkota | Subject Module | Assign Subject | Assign Subject to Teacher | Dropdown UI, Assign Button | POST /subjects/assign | subjects, teachers | Pending | 0
Sabin Devkota | Subject Module | Subject Details | Detailed View | Detail Page UI | GET /subjects/:id | subjects | Pending | 0
Sabin Devkota | Subject Module | Subject Validation | Validate Subject Data | Frontend Validation | Backend Validation | subjects | Pending | 0
Vikash Khanal | Examination | Create Exam | Add Exam | Exam Form UI | POST /exams | exams | Pending | 0
Vikash Khanal | Examination | Edit Exam | Update Exam Details | Edit Form UI | PUT /exams/:id | exams | Pending | 0
Vikash Khanal | Examination | Delete Exam | Remove Exam | Delete Button UI | DELETE /exams/:id | exams | Pending | 0
Vikash Khanal | Examination | Exam Schedule | Schedule Timetable | Schedule UI, Calendar | GET /exams/schedule | exams | Pending | 0
Vikash Khanal | Examination | Add Results | Enter Marks | Result Entry Form UI | POST /results | results | Pending | 0
Vikash Khanal | Examination | Edit Results | Update Student Marks | Edit Form UI | PUT /results/:id | results | Pending | 0
Vikash Khanal | Examination | View Results | Result Sheet | Result Table UI | GET /results/:studentId | results | Pending | 0
Vikash Khanal | Examination | Exam Validation | Validate Exam Data | Frontend Validation | Backend Validation Logic | exams | Pending | 0
Gritika Shrestha | Authentication | Login | Login Page UI | Login Form, Validation | POST /auth/login | users | Pending | 0
Gritika Shrestha | Authentication | Login | Remember Me / Forgot Password | Checkbox, Link UI | POST /auth/reset | users | Pending | 0
Gritika Shrestha | Authentication | Register | Sign-Up Page | Registration Form UI | POST /auth/register | users | Pending | 0
Gritika Shrestha | Authentication | Register | Form Validation | Error Handling UI | Validation Logic | users | Pending | 0
Gritika Shrestha | Authentication | Password Reset | Reset Password UI | Reset Form UI | POST /auth/reset | users | Pending | 0
Gritika Shrestha | Authentication | Role Access | Admin / Teacher / Student Roles | Role Selection UI | Middleware Role Check | users | Pending | 0
Gritika Shrestha | Authentication | Protected Routes | Route Guard Implementation | Protected Route UI | JWT Verification | users | Pending | 0
Gritika Shrestha | Authentication | Security | Token Refresh | Refresh Logic UI | POST /auth/refresh | tokens | Pending | 0
Punit Giri | Attendance | Daily Attendance | Mark Attendance | Attendance Form UI | POST /attendance | attendance | Pending | 0
Punit Giri | Attendance | Daily Attendance | Edit Attendance | Edit Form UI | PUT /attendance/:id | attendance | Pending | 0
Punit Giri | Attendance | Daily Attendance | View Attendance | Attendance Table UI | GET /attendance | attendance | Pending | 0
Punit Giri | Attendance | Monthly Report | Generate Monthly Report | Report Table/Chart UI | GET /attendance/monthly | attendance | Pending | 0
Punit Giri | Attendance | Attendance Summary | Auto Count & Summary | Summary Dashboard UI | GET /attendance/summary | attendance | Pending | 0
Punit Giri | Attendance | Export Attendance | Export CSV / PDF | Export Button UI | GET /attendance/export | attendance | Pending | 0
Punit Giri | Attendance | Notifications | Absence Alerts | Alert UI | POST /attendance/alerts | attendance | Pending | 0
Punit Giri | Attendance | Attendance Validation | Validate Daily Entries | Frontend Validation UI | Validation Logic | attendance | Pending | 0
Aastik Khadka | Landing Page | Home Section | Hero Banner | Hero UI, Slider | GET /landing/home | - | Pending | 0
Aastik Khadka | Landing Page | About Section | About Us Content | About Section UI | GET /landing/about | - | Pending | 0
Aastik Khadka | Landing Page | Features Section | Feature Cards | Cards UI, Responsive Design | GET /landing/features | - | Pending | 0
Aastik Khadka | Landing Page | Testimonials Section | Reviews Carousel | Carousel UI | GET /landing/testimonials | - | Pending | 0
Aastik Khadka | Landing Page | Contact Section | Contact Form | Form UI, Validation | POST /landing/contact | contacts | Pending | 0
Aastik Khadka | Landing Page | Footer | Footer Links | Footer UI | GET /landing/footer | - | Pending | 0
Aastik Khadka | Landing Page | Responsiveness | Mobile & Tablet Views | Responsive Layout | - | - | Pending | 0